## Sheet1
WM FRC 2019 Software Status - Feb 15, 2019
task | write | debug | tune | status/notes | assigned to *
non-senior programmers: identify, train, assign tasks |  |  |  | ready to start | Joshua,Pat, Trevor
teleop and auto periodic | 6 | 6 | 2 | ready to start | Trevor,Russ,Pat
driver assist sequences | 3 | 2 | 2 | ready to start: aquireDisk, deployDisk, deployBall | Russ write, Pat debug and tune
line follow state on Ras Pi | 2 | 2 | 2 | ready to start: copy tape state, rename and change to line follower | Russ
driver assist control from Pi | 2 | 2 | 2 | ready to start | Russ
1st, 2nd robot difference document (git) | 1 | 2 | 0 | waiting for 2nd build to start | Pat
1st, 2nd robot difference code switches | 2 | 1 | 0 | waiting for diff doc | Russ
pneumatics lift control | 2 | 1 | 2 | ready to start | Trevor,Pat
pneumatics disk eject control | 1 | 1 | 0 | ready to start | Trevor, Pat
lift wheel drop control | 1 | 1 | 0 | ready to start | Trevor, Pat
lift wheel drop control definition | 1 | 0 | 0 | ready to start | Luke, Jake
deployment steps document for shadows (git) | 1 | 0 | 0 | ready to start | Trevor, Joshua
Live feed to driver station | 2 | 2 | 1 | camera; Joshua has two camera samples; need to set up roborio and driver station; work with mechanical team and driver to mount | Josha
arm/wrist pose data structures and constants | 2 | 2 | 2 |  | Russ, Pat
arm/wrist PID | 2 | 2 | 2 |  | Trevor, Russ
driver assist system integration | 0 | 2 | 2 |  | Russ, Pat
Create joystick map of all functions/sequences (git) | 1 | 0 | 0 |  | Pat
program can IDs/map devices | 2 | 2 | 0 | DONE | Trevor
define arm wrist manual control behavior (git) | 1 | 0 | 0 | DONE | Pat