## Sheet1
WM FRC 2019 Software Status - Feb 11, 2019
task | write | debug | tune | status/notes | assigned to *
driver assist sequences | 3 | 2 | 2 | aquireDisk, deployDisk, deployBall | Russ write, Pat debug and tune
line follow state on Ras Pi | 2 | 2 | 2 | copy tape state, rename and change to line follower | Pat
Create joystick map of all functions/sequences (git) | 1 | 0 | 0 |  | Pat
driver assist control from Pi | 2 | 2 | 2 |  | Russ
1st, 2nd robot difference document (git) | 1 | 2 | 0 |  | Pat
1st, 2nd robot difference code switches | 2 | 1 | 0 |  | Russ
program can IDs/map devices | 2 | 2 | 0 |  | Trevor
pneumatics lift control | 2 | 1 | 2 |  | Trevor,Russ
pneumatics disk eject control | 1 | 1 | 0 |  | Trevor, Russ
lift wheel drop control | 1 | 1 | 0 |  | Trevor, Russ
define arm wrist manual control behavior (git) | 1 | 0 | 0 |  | Pat
lift wheel drop control definition | 1 | 0 | 0 |  | Luke, Jake
deployment steps document for shadows (git) | 1 | 0 | 0 |  | Trevor
Live feed to driver station | 2 | 2 | 1 | camera; identify, purchase, set up roborio and driver station | TBD
arm/wrist pose data structures and constants | 2 | 2 | 2 |  | Russ, TBD
arm/wrist PID | 2 | 2 | 2 |  | Trevor, Russ, TBD
driver assist system integration | 0 | 2 | 2 |  | Russ, Pat
dual driver mode? Reverse drive mode ? |  |  |  |  | Pat
setup i3 laptop, vscode, java, git |  |  |  |  | Joshua
teleop and auto periodic | 6 | 6 | 2 |  | Trevor,Russ,TBD
* identify/assign/setup non-senior developers
Williams, Rogers, Joshua, Trevor, Pat